## Gantt Chart
Reservation System Project Plan
PROJECT TITLE |  | Reservation System Implementation: Sauce and Spoon |  |  |  |  | COMPANY NAME | [6 empty] | Sauce and Spoon
PROJECT MANAGER |  | Andrejs Verhovods |  |  |  |  | DATE | [6 empty] | 2025-10-21
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (DAYS) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Initiation
1.1 | Research data points on reservation systems and enhancement | Carmen | 2018-01-08 | 2018-01-15 | 7 | 100% | bar: WEEK 1 W to WEEK 2 R
1.1.1 | Gather historical data on booking process | Carmen | 2018-01-15 | 2018-01-15 | 0 | 100% | bar: WEEK 2 T
1.2 | Align and evaluate stakeholders | Alex | 2018-01-15 | 2018-01-17 | 2 | 100% | bar: WEEK 2 T to WEEK 2 R
1.3 | Calculate projections and enhancements | Carmen | 2018-01-17 | 2018-01-18 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
1.4 | Interview members of the staff | Alex | 2018-01-18 | 2018-01-19 | 1 | 100% | bar: WEEK 3 M
1.4 | Create project charter (scope and goals) | Carmen | 2018-01-22 | 2018-01-26 | 4 | 100% | bar: WEEK 3 T to WEEK 3 F
1.5 | Schedule kick off meeting | Carmen | 2018-01-29 | 2018-01-29 | 0 | 100% | bar: WEEK 3 F
2 | Sourcing
2.1 | Research reservation system options | Carmen | 2018-02-02 | 2018-02-02 | 4 | 100% | bar: WEEK 4 W to WEEK 5 M
2.2 | Generate quotes and review costs | Carmen | 2018-02-05 | 2018-02-05 | 3 | 100% | bar: WEEK 4 F to WEEK 5 T
2.3 | Test out reservation systems | Makayla | 2018-02-05 | 2018-02-09 | 4 | 100% | bar: WEEK 4 F to WEEK 5 W
2.4 | Choose a reservation system | Carmen | 2018-02-05 | 2018-02-09 | 4 | 100% | bar: WEEK 5 T to WEEK 5 F
2.5 | Vendor timeline and deliverables schedule | Carmen | 2018-02-06 | 2018-02-10 | 4 | 100% | bar: WEEK 5 T to WEEK 5 F
3 | Planning
3.1 | Create contracts and statements of work for vendors | Vince | 2018-02-12 | 2018-02-15 | 3 | 100% | bar: WEEK 6 W to WEEK 6 F
3.2.1 | Message about launch date to stakeholders | Alex | 2018-02-13 | 2018-02-13 | 0 | 100% | bar: WEEK 7 T
3.3 | Project Plan Updates | Carmen | 2018-02-15 | 2018-02-28 | 13 | 100% | bar: WEEK 7 M to WEEK 9 F
3.4 | Update marketing/social media plan/calendar | Alex | 2018-02-15 | 2018-02-25 | 10 | 100% | bar: WEEK 7 R to WEEK 9 W
3.5 | Create launch day plan: staffing, troubleshooting, etc. | Alex | 2018-02-18 | 2018-02-25 | 7 | 100% | bar: WEEK 8 T to WEEK 9 W
4 | Training
4.1 | Map out seating chart/upload into software | Makayla | 2018-02-20 | 2018-02-22 | 2 | 100% | bar: WEEK 10 T to WEEK 10 W
4.2 | Train GMs on new software | Makayla | 2018-02-23 | 2018-02-23 | 0 | 100% | bar: WEEK 10 R
4.3 | Train staff on new software | Makayla | 2018-02-24 | 2018-02-24 | 0 | 100% | bar: WEEK 10 F
4.4 | Test run reservation system | Makayla | 2018-02-25 | 2018-02-25 | 0 | 100% | bar: WEEK 11 M
4.5 | Create troubleshoot/support plan | Makayla | 2018-02-20 | 2018-02-25 | 5 | 100% | bar: WEEK 10 T to WEEK 11 M
4.6 | Launch day | Carmen | 2018-03-01 | 2018-03-01 | 0 | 100% | bar: WEEK 11 M; WEEK 12 F