## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Tablets received
Generate quotes and review costs |  |  |  | 14
Create contracts and statements of work for vendors | Use past contracts for boilerplate |  |  | 5
Order tablets | Shipping updated to ~10 days |  |  | 10
Milestone: Training complete
Manager training planning |  |  |  | 5
Manager training | One day event |  |  | 1
GM meeting with staff regarding buy-in | Let Gilly plan this |  |  | 1
Waitstaff training planning |  |  |  | 5
Waitstaff training | One day event |  |  | 1
Milestone: Tablet installation complete
Book an electrician to install the tablets/wiring | Reference from Deanna |  |  | 8
Install working tablets in the bar area at the Downtown restaurant locations |  |  |  | 1
Install working tablets in the bar area at the North restaurant locations |  |  |  | 1
Sync tablet software with POS | Need to update the POS system |  |  | 7
Milestone: Launch Day complete
Create a launch day plan: staffing, troubleshooting, etc. |  |  |  | 20
Upload branding to tablets | Connect the marketing team to Terrific Tablets |  |  | 10
Load menus into the tablets | Waiting on Carter |  |  | 7
Include messaging about payment security on the tablet | Uploading text |  |  | 1
Create a behind-the-scenes video of the scratch-to-table process to show on the tablets |  |  |  | 14
Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  |  |  | 13
Create and implement a post-dining survey to assess customer satisfaction |  |  |  | 3
Test run planning |  |  |  | 10
Test run | One day event |  |  | 1
Launch day | One day event |  |  | 1

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Tablets received
Generate quotes and review costs |  | 14 | 8 | 14 | 16 | M
Create contracts and statements of work for vendors | Use past contracts for boilerplate | 5 | 3 | 5 | 7 | H
Order and receive tablets | Shipping updated to ~10 days | 10 | 8 | 10 | 12 | M
Milestone: Training complete
Manager training planning |  | 5 | 4 | 5 | 7 | M
Manager training | One day event | 1 | 1 | 1 | 2 | H
GM meeting with staff regarding buy-in | Let Gilly plan this | 1 | 1 | 1 | 2 | H
Waitstaff training planning |  | 5 | 3 | 5 | 8 | M
Waitstaff training | One day event | 1 | 1 | 1 | 2 | H
Milestone: Tablet installation complete
Book an electrician to install the tablets/wiring | Reference from Deanna | 8 | 6 | 8 | 10 | H
Install working tablets in the bar area at the Downtown restaurant locations |  | 1 | 1 | 1 | 2 | H
Install working tablets in the bar area at the North restaurant locations |  | 1 | 1 | 1 | 2 | H
Sync tablet software with POS | Need to update the POS system | 7 | 4 | 7 | 9 | L
Milestone: Launch Day complete
Create a launch day plan: staffing, troubleshooting, etc. |  | 20 | 10 | 20 | 23 | L
Upload branding to tablets | Connect the marketing team to Terrific Tablets | 10 | 6 | 10 | 13 | M
Load menus into the tablets | Waiting on Carter | 7 | 4 | 7 | 9 | L
Include messaging about payment security on the tablet | Uploading text | 1 | 1 | 1 | 3 | H
Create a behind-the-scenes video of the scratch-to-table process to show on the tablets |  | 14 | 9 | 14 | 18 | M
Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  | 13 | 7 | 13 | 17 | M
Create and implement a post-dining survey to assess customer satisfaction |  | 3 | 1 | 3 | 5 | H
Test run planning |  | 10 | 7 | 10 | 15 | L
Test run | One day event | 1 | 1 | 1 | 3 | M
Launch day | One day event | 1 | 1 | 1 | 1 | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Resource 1 | https://restaurant.org/education-and-resources/resource-library/restaurant-technology-trends-2023/ | 2025-09-28 | This National Restaurant Association article outlines tech trends and adoption tips, including tablet-based ordering. It highlights key rollout considerations like staff training, Wi-Fi upgrades, and customer education. Also emphasizes ongoing tech support post-launch.
Resource 2 | https://pos.toasttab.com/blog/on-the-line/how-to-set-up-a-restaurant-pos-system | 2025-09-28 | Blog post by Toast, a leading POS provider, offering a step-by-step POS/tablet setup guide for restaurants. Covers essentials like menu uploading, device testing, security configurations, and launch day planning. Great for checklist-style task development.

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Average ticket time – Appetizers ≤ 8 minutes, Entrées 12–15 minutes; reduce table turn time by 30 minutes | How effectively did the tablets reduce customer wait times for food orders and improve table turn times? | Average appetizer ticket time, average entrée ticket time, and average table turn time before vs. after tablets | FALSE
Customer Satisfaction | Checkout speed – Checkout completed in 1 minute or less; seamless/easy process | Did tablets improve the speed and efficiency of the checkout process for customers? | verage checkout completion time (goal: ≤ 1 minute) | FALSE
Customer Satisfaction | Tablet reliability – Less than 5% of customers report tablet technical issues weekly | What technical or usability issues did customers and staff experience with the tablets? | Percentage of customers/staff reporting technical issues (goal: < 5%) | FALSE
Customer Satisfaction | Order accuracy – 98% accuracy for customer-placed orders | To what extent did the tablets improve order accuracy and reduce incorrect orders? | Percentage of correct vs. incorrect orders (goal: ≥ 98% accuracy) | FALSE
Customer Satisfaction | Lobby wait time – Customers wait 10 minutes or less before being seated | Did the use of tablets help decrease average customer wait times in the lobby? | Average lobby wait time before seating (goal: ≤ 10 minutes) | FALSE
Ease-of-Use | Customers should find the tablets intuitive and simple to use | How easy was it to place your order using the tablet? | Average rating of ease-of-use on a 1–5 scale (target: ≥4) | FALSE
Ease-of-Use | Customers should quickly learn how to navigate the tablets | How long did it take customers to feel comfortable using the tablet? | % of customers reporting “Immediately” or “Within 5 minutes” (target: ≥80%) | FALSE
Customer Satisfaction | Guests should be satisfied with service speed during dining | How satisfied were you with the speed of service today? | Average satisfaction score on a 1–5 scale (target: ≥4) | FALSE
Customer Satisfaction | Tablets should enhance the overall dining experience | Did using the tablet improve your overall dining experience? | % of customers answering “Yes” (target: ≥80%) | FALSE
Customer Satisfaction | Guests should be willing to recommend Sauce & Spoon after using the tablets | Would you recommend Sauce & Spoon to a friend? | % of customers answering “Yes” (target: ≥85%) | FALSE
Customer Feedback | Capture customer highlights about tablet usage | What did you like most about using the tablets? | Number of positive themes/comments collected (qualitative analysis) | FALSE
Customer Feedback | Identify areas for improvement in tablet design or usability | What improvements would you suggest for the tablets? | List of improvement suggestions (qualitative analysis; tracked by frequency/theme) | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time – Appetizers ≤ 8 minutes, Entrées 12–15 minutes; reduce table turn time by 30 minutes | How effectively did the tablets reduce customer wait times for food orders and improve table turn times? | Average appetizer ticket time, average entrée ticket time, and average table turn time before vs. after tablets | Approximately how long did you wait for your food to arrive? | Multiple choice | Less than 8 minutes | 8–12 minutes | 12–15 minutes | More than 15 minutes
Checkout speed – Checkout completed in 1 minute or less; seamless/easy process | Did tablets improve the speed and efficiency of the checkout process for customers? | average checkout completion time (goal: ≤ 1 minute) | How would you rate the speed of checkout using the tablet? | Scaled | 1: Very slow | 2: Slow | 3: Neutral | 4: Fast | 5: Very fast
Tablet reliability – Less than 5% of customers report tablet technical issues weekly | What technical or usability issues did customers and staff experience with the tablets? | Percentage of customers/staff reporting technical issues (goal: < 5%) | Did you experience any technical issues while using the tablet? | Open-ended | Yes | No | If yes, describe issue
Order accuracy – 98% accuracy for customer-placed orders | To what extent did the tablets improve order accuracy and reduce incorrect orders? | Percentage of correct vs. incorrect orders (goal: ≥ 98% accuracy) | Was your food order correct when it arrived? | Yes/No | Yes | No
Lobby wait time – Customers wait 10 minutes or less before being seated | Did the use of tablets help decrease average customer wait times in the lobby? | Average lobby wait time before seating (goal: ≤ 10 minutes) | Approximately how long did you wait to be seated today? | Multiple choice | Less than 5 minutes | 5–10 minutes | 10–15 minutes | More than 15
Customers should find the tablets intuitive and simple to use | How easy was it to place your order using the tablet? | Average rating of ease-of-use on a 1–5 scale (target: ≥4) | How easy was it to place your order using the tablet? | Scaled | 1: Very difficult | 2: Somewhat difficult | 3: Neutral | 4: Somewhat easy | 5: Very easy
Customers should quickly learn how to navigate the tablets | How long did it take customers to feel comfortable using the tablet? | % of customers reporting “Immediately” or “Within 5 minutes” (target: ≥80%) | How long did it take you to feel comfortable navigating the tablet? | Multiple choice | Immediately | Within 5 minutes | More than 5 minutes | Never
Guests should be satisfied with service speed during dining | How satisfied were you with the speed of service today? | Average satisfaction score on a 1–5 scale (target: ≥4) | How satisfied were you with the speed of service today? | Scaled | 1: Very dissatisfied | 2: Dissatisfied | 3: Neutral | 4: Satisfied | 5: Very satisfied
Tablets should enhance the overall dining experience | Did using the tablet improve your overall dining experience? | % of customers answering “Yes” (target: ≥80%) | Did using the tablet improve your overall dining experience? | Yes/No | Yes | No | Not sure
Guests should be willing to recommend Sauce & Spoon after using the tablets | Would you recommend Sauce & Spoon to a friend? | % of customers answering “Yes” (target: ≥85%) | Would you recommend Sauce & Spoon to a friend based on today’s visit? | Yes/No | Yes | No
Capture customer highlights about tablet usage | What did you like most about using the tablets? | Number of positive themes/comments collected (qualitative analysis) | What did you like most about using the tablets? | Open-ended | Open-ended
Identify areas for improvement in tablet design or usability | What improvements would you suggest for the tablets? | List of improvement suggestions (qualitative analysis; tracked by frequency/theme) | What improvements would you suggest for the tablets? | Open-ended | Open-ended